## TEAM
USER | LAST NAME | FIRST NAME
Pepe | Peña Seco | Jose R.
Willy | Escovilla Biason | Willy
Sara | González Ramírez | Sara
Daniel | Díaz Martel | Daniel
Antonio | Aparicio González | Antonio

## WBS
TASK | SUBTASK | SUBTASK ESTIMATE | SUBTASK DURATION | STAGE | TASK ESTIMATE | TASK DURATION
Choose Project Idea |  |  |  | 1 | 4:00 | 3:20
| Project Decision Meeting | 4:00 | 3:20 | 1
Executive Summary |  |  |  | 2 | 19:50 | 22:41
| Base scaffold | 0:40 | 0:32 | 2
| Desicion of tools for creating summary meeting | 1:00 | 0:48 | 2
| Description of Proposal | 1:00 | 0:52 | 2
| Market and Competition | 4:00 | 4:47 | 2
| Income Sources | 2:00 | 2:26 | 2
| Stakeholders | 2:00 | 2:48 | 2
| SWOT | 2:30 | 2:38 | 2
| Product Backlog | 6:00 | 6:54 | 2
| Tools used in the document | 0:40 | 0:56 | 2
Corporative Identity Design |  |  |  | 3 | 2:00 | 2:37
| Logo | 2:00 | 2:37 | 3

## TRACKING
DATE | STARTING TIME | FINAL TIME | TASK | SUBTASK | AUTHOR | DURATION | NOTES
2024-01-30 | 11:15 | 11:56 | Choose Project Idea | Project Decision Meeting | Pepe | 0:41
2024-01-30 | 11:15 | 11:56 | Choose Project Idea | Project Decision Meeting | Willy | 0:41
2024-01-30 | 11:15 | 11:56 | Choose Project Idea | Project Decision Meeting | Sara | 0:41
2024-01-30 | 11:15 | 11:56 | Choose Project Idea | Project Decision Meeting | Daniel | 0:41
2024-01-30 | 11:20 | 11:56 | Choose Project Idea | Project Decision Meeting | Antonio | 0:36
2024-01-30 | 12:00 | 12:16 | Executive Summary | Base scaffold | Pepe | 0:16
2024-01-30 | 12:00 | 12:16 | Executive Summary | Base scaffold | Willy | 0:16
2024-01-30 | 12:00 | 12:16 | Executive Summary | Desicion of tools for creating summary meeting | Daniel | 0:16
2024-01-30 | 12:00 | 12:16 | Executive Summary | Desicion of tools for creating summary meeting | Sara | 0:16
This line has stopped working
2024-01-30 | 12:00 | 12:16 | Executive Summary | Desicion of tools for creating summary meeting | Antonio | 0:16
2024-01-31 | 18:02 | 18:28 | Executive Summary | Description of Proposal | Pepe | 0:26
2024-01-31 | 18:02 | 18:28 | Executive Summary | Description of Proposal | Willy | 0:26
2024-01-31 | 18:37 | 21:10 | Executive Summary | Market and Competition | Pepe | 2:33
2024-01-31 | 18:37 | 20:51 | Executive Summary | Market and Competition | Antonio | 2:14
2024-01-31 | 18:32 | 19:45 | Executive Summary | Income Sources | Willy | 1:13
2024-01-31 | 18:32 | 19:45 | Executive Summary | Income Sources | Daniel | 1:13
2024-01-31 | 20:00 | 20:24 | Executive Summary | Stakeholders | Willy | 0:24
2024-01-31 | 20:00 | 20:10 | Executive Summary | Stakeholders | Daniel | 0:10
2024-02-01 | 16:12 | 17:31 | Executive Summary | SWOT | Pepe | 1:19
2024-02-01 | 16:12 | 17:31 | Executive Summary | SWOT | Sara | 1:19
2024-02-01 | 17:40 | 19:58 | Executive Summary | Product Backlog | Antonio | 2:18
2024-02-01 | 17:40 | 19:58 | Executive Summary | Product Backlog | Daniel | 2:18
2024-02-01 | 17:40 | 19:58 | Executive Summary | Product Backlog | Sara | 2:18
2024-02-02 | 22:13 | 23:39 | Executive Summary | Stakeholders | Willy | 1:26
2024-02-02 | 22:13 | 23:01 | Executive Summary | Stakeholders | Daniel | 0:48
2024-02-02 | 18:00 | 18:28 | Executive Summary | Tools used in the document | Sara | 0:28
2024-02-02 | 18:00 | 18:28 | Executive Summary | Tools used in the document | Antonio | 0:28
2024-02-03 | 17:46 | 18:30 | Corporative Identity Design | Logo | Pepe | 0:44
This line has stopped working
2024-02-03 | 17:46 | 18:55 | Corporative Identity Design | Logo | Sara | 1:09
2024-02-03 | 17:46 | 18:30 | Corporative Identity Design | Logo | Willy | 0:44

## HOURS_TASK_SUBTASK
Etiquetas de fila | Suma de DURATION
(en blanco) | 0:00
(en blanco) | 0:00
Choose Project Idea | 3:20
Project Decision Meeting | 3:20
Executive Summary | 22:41
Base scaffold | 0:32
Desicion of tools for creating summary meeting | 0:48
Description of Proposal | 0:52
Market and Competition | 4:47
Income Sources | 2:26
Stakeholders | 2:48
SWOT | 2:38
Product Backlog | 6:54
Tools used in the document | 0:56
Corporative Identity Design | 2:37
Logo | 2:37
Total general | 28:38

## HOURS_PERSON_TASK
Suma de DURATION | Tarea
Etiquetas de fila | (en blanco) | Choose Project Idea | Executive Summary | Corporative Identity Design | Total general
Antonio |  | 0:36 | 5:16 |  | 5:52
Daniel |  | 0:41 | 4:45 |  | 5:26
Pepe |  | 0:41 | 4:34 | 0:44 | 5:59
Sara |  | 0:41 | 4:21 | 1:09 | 6:11
Willy |  | 0:41 | 3:45 | 0:44 | 5:10
(en blanco) | 0:00 |  |  |  | 0:00
Total general | 0:00 | 3:20 | 22:41 | 2:37 | 28:38

## HOURS_PERSON_DAY
Suma de DURATION | Miembro
Etiquetas de fila | Antonio | Daniel | Pepe | Sara | Willy | (en blanco) | Total general
(en blanco) | [5 empty] | 0:00 | 0:00
30-ene | 0:52 | 0:57 | 0:57 | 0:57 | 0:57 |  | 4:40
31-ene | 2:14 | 1:23 | 2:59 |  | 2:03 |  | 8:39
01-feb | 2:18 | 2:18 | 1:19 | 3:37 |  |  | 9:32
02-feb | 0:28 | 0:48 |  | 0:28 | 1:26 |  | 3:10
03-feb |  |  | 0:44 | 1:09 | 0:44 |  | 2:37
Total general | 5:52 | 5:26 | 5:59 | 6:11 | 5:10 | 0:00 | 28:38