## TEAM
USER | LAST NAME | FIRST NAME
Pepe | Peña Seco | Jose R.
Willy | Escovilla Biason | Willy
Saraphi | González Ramírez | Sara
DanTheMan | Díaz Martel | Daniel
Antoni | Aparicio González | Antonio

## WBS
TASK | SUBTASK | SUBTASK ESTIMATE | SUBTASK DURATION | STAGE | TASK ESTIMATE | TASK DURATION
Choose Project Idea |  |  |  | 1 | 4:00 | 3:20
| Project Decision Meeting | 4:00 | 3:20 | 1
Executive Summary |  |  |  | 2 | 1:40 | 1:20
| Base scaffold | 0:40 | 0:32 | 2
| Desicion of tools for creating summary meeting | 1:00 | 0:48 | 2

## TRACKING
DATE | STARTING TIME | FINAL TIME | TASK | SUBTASK | AUTHOR | DURATION | NOTES
2024-01-30 | 11:15 | 11:56 | Choose Project Idea | Project Decision Meeting | Pepe | 0:41
2024-01-30 | 11:15 | 11:56 | Choose Project Idea | Project Decision Meeting | Willy | 0:41
2024-01-30 | 11:15 | 11:56 | Choose Project Idea | Project Decision Meeting | Saraphi | 0:41
2024-01-30 | 11:15 | 11:56 | Choose Project Idea | Project Decision Meeting | DanTheMan | 0:41
2024-01-30 | 11:20 | 11:56 | Choose Project Idea | Project Decision Meeting | Antoni | 0:36
2024-01-30 | 12:00 | 12:16 | Executive Summary | Base scaffold | Pepe | 0:16
2024-01-30 | 12:00 | 12:16 | Executive Summary | Base scaffold | Willy | 0:16
2024-01-30 | 12:00 | 12:16 | Executive Summary | Desicion of tools for creating summary meeting | DanTheMan | 0:16
2024-01-30 | 12:00 | 12:16 | Executive Summary | Desicion of tools for creating summary meeting | Saraphi | 0:16
2024-01-30 | 12:00 | 12:16 | Executive Summary | Desicion of tools for creating summary meeting | Antoni | 0:16

## HOURS_TASK_SUBTASK
Etiquetas de fila | Suma de DURATION
(en blanco) | 0:00
(en blanco) | 0:00
Choose Project Idea | 3:20
Project Decision Meeting | 3:20
Executive Summary | 1:20
Base scaffold | 0:32
Desicion of tools for creating summary meeting | 0:48
Total general | 4:40

## HOURS_PERSON_TASK
Suma de DURATION | Tarea
Etiquetas de fila | (en blanco) | Choose Project Idea | Executive Summary | Total general
Antoni |  | 0:36 | 0:16 | 0:52
DanTheMan |  | 0:41 | 0:16 | 0:57
Pepe |  | 0:41 | 0:16 | 0:57
Saraphi |  | 0:41 | 0:16 | 0:57
Willy |  | 0:41 | 0:16 | 0:57
(en blanco) | 0:00 |  |  | 0:00
Total general | 0:00 | 3:20 | 1:20 | 4:40

## HOURS_PERSON_DAY
Suma de DURATION | Miembro
Etiquetas de fila | Antoni | DanTheMan | Pepe | Saraphi | Willy | (en blanco) | Total general
(en blanco) | [5 empty] | 0:00 | 0:00
30-ene | 0:52 | 0:57 | 0:57 | 0:57 | 0:57 |  | 4:40
Total general | 0:52 | 0:57 | 0:57 | 0:57 | 0:57 | 0:00 | 4:40